## Summary
AIA G702
APPLICATION FOR PAYMENT
|  | OWNER: |  |  |  | PROJECT: | [6 empty] | APPLICATION NUMBER: |  |  |  |  | 4
|  |  | John Malone Corp |  |  |  | Olympic World Project | [5 empty] | WORK CATEGORY NO: |  |  |  |  | 200812
|  |  | 456 Broadway |  |  |  | 345 Site Street | [5 empty] | PERIOD ENDING: |  |  |  |  | March 31, 2017
|  |  | New York, NY 12345 |  |  |  | WorkSmart, CA 12345 | [5 empty] | CONTRACT WORK: |  |  |  |  | Consulting & Site Prep
[13 empty] | PROJECT NUMBER: |  |  |  |  | 12345
|  | CONTRACTOR: |  |  |  | ARCHITECT: | [14 empty] | DISTRIBUTION:
|  |  | Big's Construction Inc. |  |  |  | New York Design Architects | [5 empty] | PERCENT COMPLETE |  |  |  |  | 55.1% |  |  | CONTRACTOR |  |  | ◄
|  |  | 1000 Pro Boulevard |  |  |  | 175 W Broadway | [13 empty] | ARCHITECT |  |  | ◄
|  |  | Anytown, USA 10001 |  |  |  | New York, NY 10013 | [5 empty] | PREPARED BY: |  |  |  |  | Julie Criptem |  |  | File |  |  | ◄
[21 empty] | Created using of Paymee. |  |  | Paymee supports printing to AIA G702
|  | APPLICATION FOR PAYMENT - SUMMARY | [11 empty] | CONTRACTOR'S CERTIFICATION:
|  | Refer to continuation sheets attached for detailed breakdown. | [11 empty] | The Contractor declares that to the best of his knowledge, information and belief the Work covered by this Application for Payment has been completed in accordance with the Contract Documents, that all amounts have been paid to him for Work for which previous Certificates for Payment were issued and payments received from the Owner, and that current payment shown herein is now due.
|  | 1. | ORIGINAL CONTRACT AMOUNT: | [6 empty] | 460000
|  | 2. | NET CHANGES TO CONTRACT: | [6 empty] | 30000
|  | 3. | TOTAL CONTRACT AMOUNT: | [6 empty] | 490000 |  |  |  | CONTRACTOR: |  |  | Barry Antone |  |  |  |  | DATE: | 2016-03-28
|  | 4. | TOTAL COMPLETED AND STORED TO DATE: | [6 empty] | 270000
|  | 5. | RETAINAGE: | [10 empty] | State: | NY |  | Country: |  | USA
|  |  | a. | 15.0 | % of Completed Work |  |  |  | 34275 |  |  |  |  | Subscribed & sworn to before me
|  |  | b. | 10.0 | % of Stored Material |  |  |  | 4150 |  |  |  |  | this | 28th | day of |  | March
|  |  | Total Retainage: | [6 empty] | 38425 |  |  |  | Notary Public Name: |  |  |  | Hillary Clifton
[14 empty] | Commission Expiration Date: | [5 empty] | 2019-05-31
|  | 6. | TOTAL COMPLETED LESS RETAINAGE: | [6 empty] | 231575
ARCHITECT'S CERTIFICATION:
|  | 7. | LESS PREVIOUS APPLICATIONS: | [6 empty] | 189975 |  |  |  | The Architect hereby confirms that based on site observations & to the best of his/her knowledge, this payment application accurately reflects the progression of work and that this work meets contract requirements sufficient enough to justify payment in the amount certified below:
|  | 8. | CURRENT PAYMENT DUE: | [6 empty] | 41600
|  | 9. | BALANCE TO FINISH INCLUDING RETAINAGE: | [6 empty] | 258425 |  |  |  | AMOUNT:
Provide explanation below or attached if amount certified does not match this application amount. Initial all figures & markups to agree with certified amount.
|  | EXTRA WORK SUMMARY |  |  |  |  | ADDITIONS |  |  |  | DELETIONS
|  | Changes From Prev Applications: |  |  |  |  | 60000 |  |  |  | 30000 | 30000 |  | ARCHITECT: | [7 empty] | DATE:
|  | Changes From This Application: |  |  |  |  | 0 | 0 |  |  | 0 | 0
|  | Total: |  |  |  |  | 60000 | 0 |  |  | 30000 | 0 |  | The Amount Certified is payable to the contractor listed above.
|  | Net Changes: | [5 empty] | 30000
Created using Paymee for Excel. www.Paymee.com.
Print to AIA G702 with Paymee
AIA G702
AIA G702
[14 empty] | Above Payment Application was created using Paymee. For more info see: | www.paymentapplication.com
This is a sample summary sheet for progress billing applications.
This sample was created using Paymee (PAYment application Made Easy for Excel) .
This is an exported Paymee sample with no formulas or automation of any kind.
Download Paymee to be able to create & update such applications in a fully automated
environment - right from Excel! Paymee saves time, prevents mistakes & doesn't require
any Excel experience!
Paymee features include:
► Paymee supports printing the Summay sheet data onto original *AIA Document G702!
See AIA.org for information on obtaining *AIA Document G702
► Paymee is flexible & not formula based!
No need to worry about formulas or accidentally overwriting them!
Update items by value -or- by % -or- by cumulative value -or- cumulative %
Customizable layout & features.
► Fully menu driven - custom 'Paymee' menu appears in Excel on loading.
Custom Right-Click menu for popular tasks.
► Paymee prevents user mistakes...
Virtually impossible to accidentally change or delete 'formulas' & automated fields!
► Summary sheet updates automatically from data on the continuation sheet...
Never enter the same piece of data in more than one place!
► New updates ('new draw') are fully automated.
► Automated & customizable retainage calculations.
► Organize applications with sub-headings & collapsible sections for easy navigation.
A free version of Paymee is available! Satisfaction guaranteed.
*AIA is a trademark of American Institute of Architects & not affiliated with Paymee nor Sapro Systems.
AIA Document G702 is a product of the American Institute of Architects.
Note on O18: The total of Scheduled Value (Column C) for base contract line items.
Note on O19: The total of Scheduled Value for extra work line items (Column C).
Note on O21: The total value of work completed to date (column G).
Note on E23: This value is applied to the total of 'Prev. App. Value' (Column D) and 'This App. Value' (Column E).
Note on E24: This value is applied to the total of This App. Stored Material (Column F).
Note on O29: The line above from the previous application. Click me for more information.
Note on O33: This is the amount remaining to bill.
Note on L36: The total of Scheduled Value for extra work additions from previous applications.
Note on P36: The total of Scheduled Value for extra work deletions from previous applications.
Note on L37: The total of Scheduled Value for extra work additions from this application.
Note on P37: The total of Scheduled Value for extra work deletions from this application.

## Detail
AIA G703 | [13 empty] | AIA G702
AIA G703
PAYMENT APPLICATION DETAIL
|  |  | FROM: | Professional Contracting Inc. |  |  |  |  | PROJECT: | Olympic World Project
|  |  | WORK: | 200812 - Consulting & Site Prep |  |  |  |  | NO: | 12345
|  |  | WORK CATEGORY |  |  | COMPLETED WORK |  |  |  |  | BALANCE TO FINISH | RETAINAGE
|  |  | Item No. | Description | Scheduled Value | Prev. App. | This App. |  | Total |  |  | Value (15%/10%)
[6 empty] | Value | Work In Place | Stored Mat. | Value | %
|  |  | A | B | C | D=Prev. (D+E) | E | F | G=D+E+F | L=G/C | H=C-G | I
Created using Paymee for Excel. Visit www.Paymee.com for more information.
Project Consulting Services
|  |  | 10 | Feasibility Study | 80000 | 74000 | 6000 |  | 80000 | 100% | 0 | 12000
|  |  | 20 | Site Analysis & testing | 20000 | 10000 | 0 | 4000 | 14000 | 70% | 6000 | 1900
|  |  | 30 | Shop Drawings | 40000 | 22500 | 9500 |  | 32000 | 80% | 8000 | 4800
|  |  | 40 | Project Website Development | 60000 | 21000 | 12000 |  | 33000 | 55% | 27000 | 4950
|  |  | 40 | Accountant Staff for Phase 1 | 25000 | 10000 | 6250 |  | 16250 | 65% | 8750 | 2437.5
|  |  | 50 | Approvals & related processing | 35000 | 10500 | 5250 |  | 15750 | 45% | 19250 | 2362.5
|  | Project Consulting Services: |  |  | 260000 | 148000 | 39000 | 4000 | 191000 | 73.46% | 69000 | 28450
Preliminary Site Work
|  |  | 40 | Site Clearance & demo | 50000 | 12500 | 5000 |  | 17500 | 35% | 32500 | 2625
|  |  | 60 | Concrete & Marble | 150000 | 0 | 0 | 37500 | 37500 | 25% | 112500 | 3750
|  | Preliminary Site Work: |  |  | 200000 | 12500 | 5000 | 37500 | 55000 | 27.5% | 145000 | 6375
EXTRA WORK SECTION 1
|  |  | A01 | Additional Board Approvals | 40000 | 32000 | 2000 |  | 34000 | 85% | 6000 | 5100
|  |  | A02 | Upgrade to USA suppliers | 20000 | 10000 | 10000 |  | 20000 | 100% | 0 | 3000
|  |  | D03 | Delete Gold Finishes | -30000 | -30000 | 0 |  | -30000 | 100% | 0 | -4500
|  | EXTRA WORK SECTION 1: |  |  | 30000 | 12000 | 12000 | 0 | 24000 | 80% | 6000 | 3600
|  | Total Base Contract Work: |  |  | 460000 | 160500 | 44000 | 41500 | 246000 | 53.48% | 214000 | 34825
|  | Total Extra Work |  |  | 30000 | 12000 | 12000 | 0 | 24000 | 93.33% | 6000 | 3600
|  | GRAND TOTAL: |  |  | 490000 | 172500 | 56000 | 41500 | 270000 | 55.1% | 220000 | 38425
Created using Paymee for Excel. Download for free at: www.Paymee.com
Note on N10: Retainage % for Work in Place & Stored Material. Select 'Settings'->'Retainage Settings' for more retainage options.
Note on I11: Value of work completed this application not including Stored Material.
Note on J11: Cumulative value of stored material not yet incorporated into the work.
Note on L11: The total percent completed. The percentage is relative to the Scheduled Value.
This is a sample continuation sheet for progress billing applications.
This sample was created using Paymee (PAYment application Made Easy for Excel) .
This is a exported Paymee sample with no formulas or automation of any kind.
Download Paymee to be able to create & update such applications in a fully automated
environment - right from Excel! Paymee saves time, prevents mistakes & doesn't require
any Excel experience!
Paymee features include:
-Paymee supports printing the summay sheet data on to *AIA Document G702!
...or print to plain paper using our alternative format.
-Fully menu driven - custom 'Paymee' menu appears in Excel on loading.
Custom Right-Click menu for popular tasks.
-Paymee is flexible & not formula based!
No need to worry about formulas or accidentally overwriting them!
Update items by value -or- by % -or- by cumulative value -or- cumulative %
Customizable layout & features.
-Paymee prevents user mistakes...
Virtually impossible to accidentally change or delete 'formulas' & automated fields!
-Summary sheet updates automatically from data on the continuation sheet...
Never enter the same piece of data in more than one place!
-New updates ('new draw') are fully automated.
-Automated & customizable retainage calculations.
-Organize applications with sub-headings & collapsible sections for easy navigation.
A free version of Paymee is available! See www.Paymee.com
*AIA is a trademark of American Institute of Architects & not affiliated with Paymee or Sapro Systems.
AIA Document G702 is a product of the American Institute of Architects.