## Continuation Sheet
AIA G703 | [14 empty] | AIA G702
AIA G703
PAYMENT APPLICATION DETAIL
|  |  |  | FROM: | Professional Contracting Inc. |  |  |  |  | PROJECT: | Olympic Bridge Project
|  |  |  | WORK: | 200812 - Consulting & Site Prep |  |  |  |  | NO: | 123456
|  |  |  | WORK CATEGORY |  |  | COMPLETED WORK |  |  |  |  | BALANCE TO FINISH | RETAINAGE
|  |  |  | Item No. | Description | Scheduled Value | Prev. App. | This App. |  | Total |  |  | Value (15%/10%)
[7 empty] | Value | Work In Place | Stored Mat. | Value | %
|  |  |  | A | B | C | D=Prev. (D+E) | E | F | G=D+E+F | L=G/C | H=C-G | I
Created using Paymee for Excel. Ideal for use where AIA G702 and G703 are required.
Project Consulting Services
|  |  |  | 10 | Feasibility Study | 80000 | 74000 | 6000 |  | 80000 | 100% | 0 | 12000
|  |  |  | 20 | Site Analysis & testing | 20000 | 10000 | 0 | 4000 | 14000 | 70% | 6000 | 1900
|  |  |  | 30 | Shop Drawings | 40000 | 22500 | 9500 |  | 32000 | 80% | 8000 | 4800
|  |  |  | 40 | Project Website Development | 60000 | 21000 | 12000 |  | 33000 | 55% | 27000 | 4950
|  |  |  | 40 | Accountant Staff for Phase 1 | 25000 | 10000 | 6250 |  | 16250 | 65% | 8750 | 2437.5
|  |  |  | 50 | Approvals & related processing | 35000 | 10500 | 5250 |  | 15750 | 45% | 19250 | 2362.5
|  |  | Project Consulting Services: |  |  | 260000 | 148000 | 39000 | 4000 | 191000 | 73.46% | 69000 | 28450
Preliminary Site Work
|  |  |  | 40 | Site Clearance & demo | 50000 | 12500 | 5000 |  | 17500 | 35% | 32500 | 2625
|  |  |  | 60 | Concrete & Marble | 150000 | 0 | 0 | 37500 | 37500 | 25% | 112500 | 3750
|  |  | Preliminary Site Work: |  |  | 200000 | 12500 | 5000 | 37500 | 55000 | 27.5% | 145000 | 6375
EXTRA WORK SECTION 1
|  |  |  | A01 | Additional Board Approvals | 40000 | 32000 | 2000 |  | 34000 | 85% | 6000 | 5100
|  |  |  | A02 | Upgrade to USA suppliers | 20000 | 10000 | 10000 |  | 20000 | 100% | 0 | 3000
|  |  |  | D03 | Delete Gold Finishes | -30000 | -30000 | 0 |  | -30000 | 100% | 0 | -4500
|  |  | EXTRA WORK SECTION 1: |  |  | 30000 | 12000 | 12000 | 0 | 24000 | 80% | 6000 | 3600
|  |  | Total Base Contract Work: |  |  | 460000 | 160500 | 44000 | 41500 | 246000 | 53.48% | 214000 | 34825
|  |  | Total Extra Work |  |  | 30000 | 12000 | 12000 | 0 | 24000 | 93.33% | 6000 | 3600
|  |  | GRAND TOTAL: |  |  | 490000 | 172500 | 56000 | 41500 | 270000 | 55.1% | 220000 | 38425
AIA G703
AIA G703
[7 empty] | Above payment schedule was created using Paymee. For more info see: | www.paymentapplication.com
This is a sample continuation sheet for progress billing applications.
This sample was created using Paymee (Payment application Made Easy for Excel) .
This is a exported Paymee sample with no formulas or automation of any kind.
Download Paymee to be able to create & update such applications in a fully automated
environment - right from Excel! Paymee saves time, prevents mistakes & doesn't require
any Excel experience!
Paymee features include:
► Paymee supports printing the summay sheet data on to *AIA Document G702!
...or print to plain paper using our alternative format.
► Fully menu driven - custom 'Paymee' menu appears in Excel on loading.
Custom Right-Click menu for popular tasks.
► Paymee is flexible & not formula based!
No need to worry about formulas or accidentally overwriting them!
Update items by: value or % or cumulative value or quanitity
► Customizable layout & features. New: Support for Unit Price items
► Paymee prevents user mistakes...
Virtually impossible to accidentally change or delete 'formulas' & automated fields!
► Summary sheet updates automatically from data on the continuation sheet...
Never enter the same piece of data in more than one place!
► New updates ('new draw') are fully automated.
► Automated & customizable retainage calculations.
► Organize applications with sub-headings & collapsible sections for easy navigation.
► Paymee is free to try and Satisfaction guranteed or your money back!
*AIA is a trademark of American Institute of Architects & not affiliated with Sapro Systems.
AIA Document G702 is a product of the American Institute of Architects.
Note on N10: Retainage % for Work in Place & Stored Material. Select 'Settings'->'Retainage Settings' for more retainage options.
Note on I11: Value of work completed this application not including Stored Material.
Note on J11: Cumulative value of stored material not yet incorporated into the work.
Note on L11: The total percent completed. The percentage is relative to the Scheduled Value.